## Assignment 1 Workplan
Team Name: | Team 3, Ella, Bana, Alexis, and Nicolas
Total time taken: | <For the last submission, enter the total number of hours it took the team to complete the assignment in this cell>
Number | Task Description | Estimated time (hrs) | Assigned to | Planned Completion Date | Review completed? | Status
1 | Identify & Define the pricipal entities | 1 | Group | 2025-09-19 | Yes | Done
2 | Assign short names to entities | 0.05 | Bana & Ella | 2025-09-22 | Yes | Done
3 | Identify known quantities | 0.5 | Bana & Ella | 2025-09-20 | Yes | Done
4 | Identify the relationships | 0.75 | Bana & Ella | 2025-09-20 | Yes | Done
5 | Decide cardinality and optionality | 0.4 | Alexis | 2025-09-22 | Yes | Done
6 | Review plan & assignment requires before mockup | 0.5 | Group | 2025-09-23 | Yes | Done
7 | CRUD analysis | 2 | Alexis & Nicolas | 2025-09-26 | No | Started in class
7 | Mockup ERDs | 1.5 | Group | 2025-09-23 | Yes | Done
8 | Review and Edit Entity/Defination Matrix & Cardinality | 0.85 | Alexis, Bana, & Ella | 2025-09-26 | Yes | Done
8 | Review CRUD analysis | 0.5 | Bana & Ella | 2025-09-26 | No | Not-Started
8 | Final ERD | 2 | Ella & Bana | 2025-09-26 | Yes | Done
9 | Review Final ERD | 1 | Group | 2025-09-26 | Yes | Done
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to list all the tasks that will be required to complete this assignment. If you find new ones along the way, add them.
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to estimate how many hours you think it will take to complete this task.
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to indicate who will do the work. Indicate a name or Group.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to indicate when the initial version of this task will be completed and ready for someone else / or the team to review.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to indicate if the someone else on the team or the whole team has reviewed the work for this item.
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to enter a status like, Not Started, In-Progress, or Complete