## Assignment 1 Workplan
Team Name: | Team 3, Ella, Bana, Alexis, and Nicolas
Total time taken: | <For the last submission, enter the total number of hours it took the team to complete the assignment in this cell>
Number | Task Description | Estimated time (hrs) | Assigned to | Planned Completion Date | Review completed? | Status
1 | Physical Model Typing & Constraints | 1 | Bana | 2025-10-10 | Yes | Done
2 | Workplan | 0.25 | Ella | 2025-10-10 | Yes | Done
3 | Entity Attribute Table Information | 1 | Group | 2025-10-10 | Yes | Done
4 | Transfer A02 Entity Attribute Table ^ | 0.25 | Nicolas | 2025-10-10 | Yes | Done
5 | After Lab
6 | Add Missing Database Values to Diagram | 0.5 | Ella | 2025-10-15 | Yes | Done
7 | Add Missing Database Values to Excel Sheet | 0.5 | Alexis | 2025-10-14 | Yes | Done
8 | Review Diagram Before Database | 0.5 | Bana & Nicolas | 2025-10-15 | Yes | Done
6 | Create Database with ERDPlus SQL | 0.25 | Ella | 2025-10-16 | Yes | Done
7 | Identify and Fix Small Database Issues | 0.5 | Group | 2025-10-16 | Yes | Done
7 | Configure Database Constraints | 1 | Bana & Ella | 2025-10-16 | Yes | Done
8 | Configure Database OnDelete | 1 | Alexis & Nicolas | 2025-10-16 | Yes | Done
9 | Add Database Sequences | 0.75 | Ella | 2025-10-17 | Yes | Done
9 | Add Database Owners | 1 | Ella | 2025-10-17 | Yes | Done
10 | Add Database Dogs | 1 | Bana | 2025-10-17 | Yes | Done
11 | Add Database Vaccines | 0.5 | Alexis | 2025-10-17 | Yes | Done
12 | Add Database Reservations | 0.5 | Nicolas | 2025-10-17 | Yes | Done
13 | Appendix Queries | 0.5 | Alexis, Bana, & Ella | 2025-10-17 | Yes | Done
7 | ChangeLog | 0.5 | Group | 2025-10-17 | Yes | Done
8
8
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to list all the tasks that will be required to complete this assignment. If you find new ones along the way, add them.
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to estimate how many hours you think it will take to complete this task.
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to indicate who will do the work. Indicate a name or Group.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to indicate when the initial version of this task will be completed and ready for someone else / or the team to review.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to indicate if the someone else on the team or the whole team has reviewed the work for this item.
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use this column to enter a status like, Not Started, In-Progress, or Complete